DELIVERY ORDER

Under Indefinite Delivery/Indefinite Quantity Contract

| FIELD | VALUE |
| --- | --- |
| Delivery Order Number | N00164-25-F-0003 (DO-0003) |
| MAC Contract Number | N0016426RMP01 |
| MAC Title | Mobility MAC Follow-On |
| DO Title | JLTV Hybrid-Electric Drive (HED) Powertrain Prototype |
| Technology Area | TA1 - Powertrain Performance Prototyping |
| Issuing Office | NSWC Crane, Mobility Systems Engineering Branch (MXPQ) Naval Surface Warfare Center 300 Highway 361, Crane, IN 47522-5001 |
| Contracting Officer | Ashley Bechtel ashley.n.bechtel2.civ@us.navy.mil ¦ 812-381-7233 |
| Government PM / COR | Nicole Jacobs, NSWC Crane MXPQ nicole.jacobs.civ@us.navy.mil |
| Contractor | Meridian Drive Systems, LLC 4820 Industrial Pkwy, Columbus, IN 47201 |
| Contractor PM | Derek Wahl, P.E. dwahl@meridiandrivesystems.com ¦ 812-555-0184 |
| Contract Type | Firm Fixed Price (FFP) |
| DO Value | $3,184,500.00 |
| Period of Performance | 01 October 2024 – 31 March 2026 (18 months) |
| Award Date | 24 September 2024 |
| Accounting / ACRN | AA: $3,184,500.00 ¦ PE 0603801N ¦ PN N2478825WX15302 |

# 1. Scope of Work

This Delivery Order tasks Meridian Drive Systems, LLC to design, develop, fabricate, and test a Hybrid-Electric Drive (HED) powertrain prototype for integration onto a Government-Furnished Equipment (GFE) Joint Light Tactical Vehicle (JLTV) platform. The prototype shall demonstrate improved fuel efficiency, silent watch capability, and auxiliary power output over the baseline JLTV powertrain configuration.

The effort shall proceed through Preliminary Design Review (PDR), Critical Design Review (CDR), prototype fabrication and integration, and acceptance testing in accordance with the test plan approved by the Government. Final deliverables include the integrated prototype, Technical Data Package (TDP), test report, and all CDRLs specified herein.

# 2. Key Performance Parameters (KPPs)

| Parameter | Threshold (Minimum) | Objective (Target) |
| --- | --- | --- |
| Peak Torque Output (lb-ft) | 650 | 720 |
| Fuel Efficiency Improvement vs. Baseline (%) | 18% | 25% |
| Silent Watch Duration (hours at rated APU load) | 4.0 hrs | 6.0 hrs |
| Auxiliary Power Output (kW) | 10 kW | 15 kW |
| Thermal Rejection Compliance (MIL-STD-810) | Pass | Pass with margin |
| System Weight Increase vs. Baseline (lbs) | < 400 lbs | < 300 lbs |

# 3. Contract Data Requirements List (CDRLs)

| CDRL | Title | Frequency | Due |
| --- | --- | --- | --- |
| A001 | Engineering Presentation (PDR, CDR, TIM) | As required | Per schedule |
| A002 | Specification Requirement Verification Matrix | At PDR / CDR | Per schedule |
| A003 | Risk Identification and Mitigation Report | Monthly | 20th of month |
| A004 | Design Data (3D Models, Drawings) | At CDR | Per schedule |
| A005 | CAE Report (FEA, Thermal, Dynamics) | At CDR | Per schedule |
| A006 | Certificate of Compliance | At delivery | With prototype |
| A007 | Integration Summary Report | At delivery | With prototype |
| A008 | Technical Data Package (TDP) | At closeout | 30 Mar 2026 |
| A011 | Test Plan | 60 days pre-test | Per schedule |
| A012 | Test/Inspection Report | At test completion | Per schedule |
| A013/14/15 | Conference Agenda / Minutes / Presentation | Per meeting | 5 days after |

# 4. Schedule (Baseline)

| Milestone | Planned Date | Status at Award |
| --- | --- | --- |
| Contract Award / DO Effective | 24 Sep 2024 | Complete |
| Kickoff Meeting | 15 Oct 2024 | Planned |
| PDR Package Submission | 15 Dec 2024 | Planned |
| PDR Conduct | 10 Jan 2025 | Planned |
| CDR Package Submission | 15 Apr 2025 | Planned |
| CDR Conduct | 06 May 2025 | Planned |
| Fabrication Complete / Integration Begins | 01 Aug 2025 | Planned |
| GFE Vehicle Receipt and Integration | 15 Aug 2025 | GFE delivery pending |
| Test Plan Submission (CDRL A011) | 15 Aug 2025 | Planned |
| Acceptance Testing | 15 Sep – 15 Oct 2025 | Planned |
| Prototype Final Delivery | 01 Nov 2025 | Planned |
| All CDRLs / TDP Closeout | 31 Mar 2026 | Planned |

Issued by authority of the Contracting Officer:

Ashley Bechtel, Contracting Officer, NSWC Crane

N0016426RMP01 / DO-0003 | Award Date: 24 September 2024