MONTHLY STATUS REPORT

Month 12 of 12 — 01 September 2025 – 30 September 2025

| Contract Information |  |  |
| --- | --- | --- |
| Contract No.: | N00173-25-C-XXXX |  |
| Solicitation No.: | N0017325R24400002 |  |
| Contractor: | Apex Systems Engineering, Inc. |  |
| Program: | C4ISR Systems Design and Development |  |
| Reporting Period: | 01 September 2025 – 30 September 2025 |  |
| Contracting Officer: | Callan T. Walsh |  |
| COR: | NRL Code 8101.1 |  |
| Contractor PM: | Dr. Raymond Okafor, Apex Systems Engineering, Inc. |  |

# 1. Financial Summary (CDRL A001, Item 1–6)

| Item | Value |
| --- | --- |
| Total Amount Funded (Contract) | $8,450,000 |
| Total Amount Invoiced to Date | $5,133,380.00 |
| Total Amount Invoiced — This Period | $503,780.00 |
| Estimated Cost to Complete | $3,316,620.00 |
| ACRN Breakdown | See Attachment — ACRN Proration Schedule |

# 2. Schedule Status (CDRL A001, Item 7)

ON SCHEDULE (Extended PoP) — Modification Executed

# 3. Technical Progress (CDRL A001, Item 8)

The contract Period of Performance extension was formally executed on 08 September 2025 via Modification P00001 to contract N00173-25-C-XXXX. The modification extends the base period PoP by 90 days (to 30 December 2025) on a no-cost basis, documenting the GFI delay as the Government-caused basis for the extension. The extension allows the contractor to complete all affected Task Area 4 and Task Area 5 milestones within the adjusted schedule.

Month 12 represented a strong close to the original base year timeline. Task Area 4 (Prototype Development) completed Phase 1 integration successfully, with the prototype achieving first-power-on on 22 September 2025 — a significant technical milestone. Initial functional checkout confirmed all GFI-independent subsystems performing within specification. Task Area 5 test planning was completed and the test plan (CDRL A003) was submitted to the COR on 26 September 2025.

Cost performance at the close of the original base year is favorable: cumulative costs of $5,133,380 represent approximately 60.7% of the total funded amount, broadly consistent with approximately 10 months of billable technical work (accounting for the administrative Month 1 and the GFI-driven pace reduction in Months 9–10). No cost overrun risk is identified; the contractor projects completing the full base year scope within the funded ceiling.

The contractor formally acknowledges the Government's prompt action in executing the PoP extension modification and looks forward to completing remaining deliverables in the 90-day extension period.

# 4. Significant Accomplishments (CDRL A001, Item 8)

- PoP extension (90 days) executed via Mod P00001 on 08 September 2025

- Task Area 4: Prototype Phase 1 integration complete; first-power-on achieved 22 September 2025

- Task Area 5: Test plan (CDRL A003) submitted to COR 26 September 2025

- Prototype initial functional checkout successful — all GFI-independent subsystems in spec

- Cumulative cost at 60.7% of funded ceiling — favorable cost performance

- CDRL A002 (Milestone Chart) submitted 30 September 2025

# 5. Briefs/Reports Generated (CDRL A001, Item 9)

CDRL A003 (System Test Plan) submitted 26 September 2025. CDRL A002 submitted 30 September 2025.

# 6. Travel Activity (CDRL A001, Item 10)

None this period.

# 7. Plans for Next Month (CDRL A001, Item 11)

Extension period priorities: complete prototype Phase 2 integration and testing; conduct end-to-end system test (Task Area 5); deliver all remaining CDRLs; prepare for Option Year 1 transition if exercised.

# 8. Technical Problem Areas and Potential Solutions (CDRL A001, Item 12)

No technical problem areas to report. All active issues (GFI delay, staffing gap) have been fully resolved. Contract is on track to complete all base year scope within the 90-day extension period and within the funded ceiling.

N00173-25-C-XXXX | Apex Systems Engineering, Inc. | Month 12 Status Report | 01 September 2025 – 30 September 2025