QUARTERLY PROGRESS REPORT — Q3

Contract N0024426C0087 | ClearOps Systems LLC | NPS NATO VM Support Services

| Reporting Period: | 01 October 2026 – 31 December 2026 | Date Submitted: | 09 January 2027 |
| --- | --- | --- | --- |
| Program Manager: | Nicole Jacobs | PCO: | Noni Arcilla |
| COR: | Dr. Raymond Castillo, NPS Faculty | Overall Status: | On Track |

EXECUTIVE SUMMARY

Quarter 3 saw ClearOps Systems LLC complete delivery of all three priority course VM environments and begin substantive development of the remaining five course environments (Network Vulnerability Assessment, Cyber Incident Handling & Disaster Response, ML&AI for Cyber Applications, Introduction to ML&AI, and Network Security). The contractor provided SME support for three additional in-residence class weeks. Finalized versions of student and instructional guides for the three priority courses were accepted by NPS. The program remains on budget and on schedule.

KEY ACCOMPLISHMENTS – Q3

•  Mobile Applications VM environment (CDRL A003) delivered to NPS on 10 October 2026; passed pre-class testing on 17 October 2026. Supported 24 students at 96.8% availability during in-residence week.

•  Provided in-residence support at NSO Oberammergau for Mobile Applications class (26–30 October 2026), Network Vulnerability Assessment class (10–14 November 2026), and Cyber Incident Handling class (01–05 December 2026).

•  Accepted final versions of student and instructional guides for Network Traffic Analysis, Software Reverse Engineering, and Mobile Applications courses (CDRL A005) — approved by NPS COR on 03 November 2026.

•  Exported OVA-format VM archives for all three completed environments (CDRL A003 deliverable); government confirmed successful instantiation on alternate platforms (NPS VMware infrastructure).

•  Began development of ML&AI for Cyber Applications VM; TensorFlow, PyTorch, Jupyter environment scaffolding complete.

•  Began development of Network Vulnerability Assessment VM; Nessus, OpenVAS, Metasploit framework integration 40% complete.

•  Addressed all 3 high-priority feedback items from Network Traffic Analysis Q2 class: updated Elastiflow configuration, revised two lab exercises, and corrected SiLK netflow parsing error.

•  Delivered CDRL A006 Q3 update package documenting all revisions and version history.

WORK IN PROGRESS

•  ML&AI for Cyber Applications VM: 55% complete.

•  Introduction to ML&AI VM: 30% complete.

•  Network Vulnerability Assessment VM: 40% complete.

•  Cyber Incident Handling & Disaster Response VM: 25% complete.

•  Network Security VM: scoping and requirements review complete; development begins Q4.

ISSUES / RISKS / CORRECTIVE ACTIONS

| Issue: | Faculty feedback for Cyber Incident Handling class identified a gap in the CSIRR module: existing lab scenarios did not reflect current incident response frameworks (NIST SP 800-61 Rev. 3). |
| --- | --- |
| Severity: | Moderate |
| Mitigation: | ClearOps revised two lab scenarios to align with updated NIST guidance. Updated materials submitted to NPS COR on 19 December 2026. Flagged as high-priority per faculty; 100% addressed prior to next class cycle. |
| Status: | Resolved |

PLANNED ACTIVITIES – NEXT QUARTER

•  Complete and deliver ML&AI and Introduction to ML&AI VM environments.

•  Complete and deliver Network Vulnerability Assessment and Cyber Incident Handling VM environments.

•  Begin and complete Network Security VM.

•  Conduct in-residence support for ML&AI class (January 2027).

•  Deliver final CDRL A004 (VMs for All Classes) package.

•  Complete base year performance and prepare transition documentation for Option Year 1.

MILESTONE STATUS

| Milestone | Planned Date | Actual/Est. | Status |  |
| --- | --- | --- | --- | --- |
| Mobile Apps VM – NPS Delivery | 15 Oct 2026 | 10 Oct 2026 | Complete |  |
| In-Residence Support – Mobile Apps | 26 Oct 2026 | 26 Oct 2026 | Complete |  |
| Instructional Guides – Final Acceptance | 31 Oct 2026 | 03 Nov 2026 | Complete |  |
| OVA Export – Priority 3 VMs | 15 Nov 2026 | 20 Nov 2026 | Complete |  |
| In-Residence Support – CSIRR | 01 Dec 2026 | 01 Dec 2026 | Complete |  |
| NIST SP 800-61 Rev 3 Lab Update | 19 Dec 2026 | 19 Dec 2026 | Complete |  |
| ML&AI VM – Delivery | 31 Jan 2027 | In Progress | On Track |  |

FINANCIAL STATUS

| CLIN | Budgeted | Plan to Date | Actual to Date | Notes |
| --- | --- | --- | --- | --- |
| CLIN 0001 – VM Services | $487,200 | $365,400 | $348,200 | Tracking well; minor savings on SME labor hours in Q3. |
| CLIN 0002 – Travel | $18,400 | $18,400 | $17,850 | No additional travel Q3; NSO trip completed in Q2. |
| Total (Base Year) | $505,600 | $383,800 | $366,050 |  |

CERTIFICATION

I certify that the information contained in this Quarterly Progress Report is accurate and complete to the best of my knowledge.

| Nicole Jacobs Program Manager, ClearOps Systems LLC Date: 09 January 2027 | Dr. Raymond Castillo Contracting Officer's Representative Naval Postgraduate School Date: _______________ |
| --- | --- |