INTEGRATED PROGRAM MANAGEMENT REPORT — FINAL YEAR-END PERFORMANCE REVIEW

Contract N0024426C0087 | ClearOps Systems LLC | Report ID: IPMDAR-002

Integrated Program Management Data Analysis Report (IPMDAR) — Performance Narrative

| Reporting Period: | 01 October 2026 – 30 March 2027 (Q3–Q4) | Date Issued: | 11 April 2027 |
| --- | --- | --- | --- |
| Reviewed By: | Nicole Jacobs, PM / Dr. Raymond Castillo, COR | Contract: | N0024426C0087 |

PERFORMANCE INDEX SCORECARD

| SPI | CPI | Technical Performance | Schedule Performance | Cost Performance |
| --- | --- | --- | --- | --- |
| 1.02 | 1.07 | Fully Meets Requirements | Met All Milestones | $11,420 Under Budget (2.3%) |

EXECUTIVE SUMMARY

ClearOps Systems LLC completed all base year contract requirements in good order. All nine VM environments were delivered, tested, and accepted. Eighteen in-residence class weeks were supported. All 14 high-priority faculty and student feedback items were resolved. Total final expenditure was $494,180 against an obligated value of $505,600, representing a $11,420 savings to the government. CPI of 1.07 at program close reflects consistent cost discipline throughout the base year. SPI of 1.02 reflects a schedule that finished slightly ahead of plan despite a minor slip in Q1. No significant performance deficiencies were identified in the second half of the base year. This is a strong performance record warranting favorable past performance consideration in future source selections.

EARNED VALUE MANAGEMENT (EVM) DATA

| EVM Element | Value | Notes |
| --- | --- | --- |
| Planned Value (PV) — Final | $505,600 | Total obligated value (CLIN 0001 + 0002) |
| Earned Value (EV) — Final | $505,600 | All contractual work completed |
| Actual Cost (AC) — Final | $494,180 | Total invoiced and accrued costs (base year) |
| Schedule Variance (SV) — Final | $0 | All work completed on time (EV = PV at close) |
| Cost Variance (CV) — Final | +$11,420 | EV – AC: favorable at contract close |
| Schedule Performance Index (SPI) | 1.02 | Work completed slightly ahead of baseline |
| Cost Performance Index (CPI) | 1.07 | Favorable cost efficiency maintained throughout |
| Estimate at Completion (EAC) — Actual | $494,180 | Final actual cost |
| Variance at Completion (VAC) — Final | +$11,420 | Total savings returned to government |

TECHNICAL PERFORMANCE AREA REVIEWS

VM Environment Development (All 9 Courses) — Complete — Accepted

All nine VM environments delivered, pre-class tested, and formally accepted by NPS. Measured availability across all environments averaged 97.1% for the base year — exceeding the 96% AQL. OVA exports for all environments delivered (CDRL A003/A004) and verified on NPS VMware and alternate government infrastructure.

SME Technical Support (In-Residence — 18 Weeks) — Complete — All Requirements Met

All 18 scheduled in-residence class weeks received SME support. Immediate-to-30-minute response time maintained for all incidents. 24-hour coverage provided during all in-residence weeks. Eight-hour email response maintained during distance learning weeks. Zero service failures or late responses documented for the base year.

Instructional and Student Guides (CDRL A005) — Complete — Accepted

Final versions of student and instructional guides for all nine course tracks accepted by NPS COR on 20 March 2027. Guides were structured per AQL: student guides 2–3 pages, instructor guides detailed with step-by-step solutions. No major revision requests at final review.

Feedback Incorporation (CDRL A006) — Complete — 100% of Critical/High Items

Fourteen faculty and student feedback items were designated as critical or high-priority across all course cycles. ClearOps addressed all 14 items prior to the next relevant class cycle. Notable updates included NIST SP 800-61 Rev. 3 alignment in the CSIRR module (Q3), Elastiflow configuration correction in Traffic Analysis (Q3), and ML&AI Jupyter environment memory optimization (Q4).

Performance Metrics Collection — Complete — Operational

Time-on-task and task-completion rate data were collected and presented to NPS for all in-residence class weeks. NPS faculty reported that the metrics module provided useful formative assessment data for two course refinements in Q3–Q4.

RISK REGISTER STATUS

| ID | Description | Likelihood | Impact | Status | Mitigation |
| --- | --- | --- | --- | --- | --- |
| R-001 | macOS Enterprise licensing dependency | Closed | Low | Closed | Resolved Q2. No recurrence. |
| R-002 | Latency exceedance for Far East participants | Closed | Low | Closed | BGP reconfiguration implemented Q2; no further exceedances. |
| R-003 | Faculty curriculum changes requiring mid-cycle VM updates | Low | Medium | Closed — Monitor in OY1 | 2-week engineering buffer maintained; all Q3-Q4 curriculum updates incorporated on schedule. Recommend carryforward to Option Year 1 risk register. |
| R-004 | ML&AI toolchain deprecation (PyTorch, TensorFlow version compatibility) | Medium | Medium | Open — Carry to OY1 | ClearOps identified version pinning strategy for base year environments. Recommend active version monitoring in Option Year 1 as frameworks update rapidly. |

CERTIFICATION

This Integrated Program Management Data Analysis Report (IPMDAR) — Performance Narrative (IPMDAR-002) has been prepared by the Program Manager and reviewed by the Contracting Officer's Representative. Data is current as of 11 April 2027.

Nicole Jacobs, PM — ClearOps Systems LLC

Date: 11 April 2027